## TimelineData
Task Name | Start Date | End Date | Type | Color | Swimlane
DISCOVERY | 2025-02-20 | 2025-03-03 | Phase | Blue
MVP scope workshops | 2025-02-20 | 2025-03-03 | Feature | Green | Sprint 0
Solution Design | 2025-02-22 | 2025-03-03 | Feature | Green | Configuration
Planning | 2025-02-27 | 2025-03-03 | Feature | Green | Pre-Prod
Foundational Design | 2025-02-27 | 2025-03-03 | Feature | Green | Configuration
BUILD | 2025-03-06 | 2025-05-05 | Phase | Blue
Sprint 1 Prep. | 2025-03-06 |  | Milestone | Green | Pre-Prod
Env. Setup | 2025-03-06 | 2025-03-10 | Feature | Green | Pre-Prod
Foundational Design | 2025-03-06 | 2025-03-10 | Feature | Green | Pre-Prod
Platform configuration (Content Hub & Chili Publisher) | 2025-03-13 | 2025-05-05 | Feature | Grey | Pre-Prod
Customization & Integrations | 2025-03-13 | 2025-05-05 | Feature | Grey | Pre-Prod
Smart Templates design & build | 2025-03-13 | 2025-05-05 | Feature | Grey | Pre-Prod
Asset Migration | 2025-04-10 | 2025-05-05 | Feature | Grey | Pre-Prod
Training Materials | 2025-04-24 | 2025-05-05 | Feature | Grey | Pre-Prod
ROLLOUT | 2025-05-08 | 2025-05-26 | Phase | Grey
UAT & Stabilization | 2025-05-08 | 2025-05-19 | Feature | Grey | Pre-Prod
Training | 2025-05-08 | 2025-05-19 | Feature | Grey | Configuration
Launch | 2025-05-22 |  | Milestone | Grey | Pre-Prod
Global rollouts planning | 2025-04-04 | 2025-05-05 | Feature | Grey | Release
Scope & Design | 2025-05-08 | 2025-05-19 | Feature | Grey | Release
Solution Evolution & Global Rollout | 2025-06-05 | 2025-07-21 | Feature | Grey | Release