## Slide 1
25-Aug
01-Sep
08-Sep
15-Sep
22-Sep
29-Sep
06-Oct
13-Oct
20-Oct
27-Oct
03-Nov
10-Nov
17-Nov
24-Nov
01-Dec
08-Dec
15-Dec
22-Dec
29-Dec
05-Jan
12-Jan
19-Jan
Today
DISCOVERY
14 days
BUILD
60 days
ROLLOUT
18 days
Sprint 0
Configuration
MVP scope workshops
14 d
20 Aug - 03 Sep
Solution Design
12 d
22 Aug - 03 Sep
Foundational Design
7 d
27 Aug - 03 Sep
Training
11 d
08 Nov - 19 Nov

## Slide 2
25-Aug
01-Sep
08-Sep
15-Sep
22-Sep
29-Sep
06-Oct
13-Oct
20-Oct
27-Oct
03-Nov
10-Nov
17-Nov
24-Nov
01-Dec
08-Dec
15-Dec
22-Dec
29-Dec
05-Jan
12-Jan
19-Jan
Today
DISCOVERY
14 days
BUILD
60 days
ROLLOUT
18 days
Pre-Prod
Release
Planning
7 d
27 Aug - 03 Sep
Sprint 1 Prep.
06-Sep
Env. Setup
4 d
06 Sep - 10 Sep
Foundational Design
4 d
06 Sep - 10 Sep
Platform configuration (Content Hub & Chili Publisher)
53 d
13 Sep - 05 Nov
Customization & Integrations
53 d
13 Sep - 05 Nov
Smart Templates design & build
53 d
13 Sep - 05 Nov
Asset Migration
26 d
10 Oct - 05 Nov
Training Materials
12 d
24 Oct - 05 Nov
UAT & Stabilization
11 d
08 Nov - 19 Nov
Launch
22-Nov
Global rollouts planning
32 d
04 Oct - 05 Nov
Scope & Design
11 d
08 Nov - 19 Nov
Solution Evolution & Global Rollout
47 d
05 Dec - 21 Jan
Slide 2